## Sheet1
Task | Baseline | Target Date | Status | Remark
Release 1 |  |  |  | time user for design process flow
Group 1 |  |  | on uat
Group 3 |  | 2022-06-13 | on dev 80% | Include group5
Group 4 |  |  | on uat
SIT |  | 13/6/2022 - 16/6/2022 |  | Group3 only
UAT |  | 20/6/2022 - 24/6/2022 |  | Group1,3,4
Deploy Production |  | 2022-06-27 |  | Program only
Production |  | 2022-06-29
Deliverable Software is .. Group 1,3,4
Release 2
Req |  | 2022-06-15 |  | wait for rm 26
Group 2 (Change to 8 Report) |  |  | wait for req | move to R2.1
Group 5 |  |  | on dev 60% | include group3
Group 6 |  | ?? - 30/6/2022 | 30% on dev (2/6) | get rm on 10/6/2022 (28,30) wait for rm 26
SIT |  | 4/7/2022 - 8/7/2022
Prepare UAT
UAT |  | 11/7/2022-15/7/2022
Prepare Production
Production |  | 2022-07-21
Release 2.1
Req |  | 13/6/2022 - 17/6/2022 |  | report 8
Dev |  | 25/7/2022 - 25/8/2022 |  | report 8 + (28,30, 26) 3 report/week
SIT |  | 29/8/2022 - 2/9/2022
Prepare UAT |  | 5/9/2022 - 7/9/2022
UAT |  | 8/9/2022 - 16/9/2022
Production |  | 2022-09-19
Deliverable Software is .. Group 6 (Extend 8) |  |  |  | Switch from group 2